## small power & lighting
Dated : 03 Mar 2013
small power & lighting
level | 1st fix | final fix | Remarks
7 | done | balance partial
8 | done | balance partial
9 | done | balance partial
10 | done | balance partial
11 | done | balance partial
12 | done | balance partial
13 | done | balance partial
14 | done | balance partial
15 | done | balance partial
16 | done | done
17 | done | done
18 | done | done
19 | done | done
20 | done | done
21 | done | done
22 | done | done
23 | done | balance partial
24 | done | balance partial
25 | done | balance partial
26 | done | balance partial
27 | done | balance partial
28 | done | balance partial
29 | done | balance partial
30 | done | balance partial
31 | done | balance partial
32 | done | balance partial
33 | done | done
34 | done | done
35 | done | done
36 | done | done
37 | done | done
38 | done | done
39 | done | done
40 | done | done
41 | done | done
42 | done | done
43 | done | done
44 | done | done
45 | done | done
46 | done | done
47 | done | done

## fire alarm
Dated : 03 Mar 2013
fire alarm
level | 1st fix | commisioning for loops | final fix( insulation) | Remarks
7 | done | done
8 | done | done
9 | done | done
10 | done | ongoing
11 | done | ongoing
12 | done | ongoing
13 | done | ongoing
14 | done | ongoing
15 | done | done
16 | done | done
17 | done | done
18 | done | done
19 | done | done
20 | done | done
21 | done | done
22 | done | done
23 | done | done
24 | done | to be checked by cesco
25 | done | to be checked by cesco
26 | done | to be checked by cesco
27 | done | to be checked by cesco
28 | done | to be checked by cesco
29 | done | to be checked by cesco
30 | done | to be checked by cesco
31 | done | to be checked by cesco
32 | done | to be checked by cesco
33 | done | to be checked by cesco
34 | done | to be checked by cesco
35 | done | to be checked by cesco
36 | done | to be checked by cesco
37 | done | to be checked by cesco
38 | done | to be checked by cesco
39 | done | to be checked by cesco
40 | done | to be checked by cesco
41 | done | to be checked by cesco
42 | done | to be checked by cesco
43 | done | to be checked by cesco
44 | done | to be checked by cesco
45 | done | to be checked by cesco
46 | done | to be checked by cesco
47 | under review

## tele& data
Dated : 03 Mar 2013
tele & data
level | 1st fix | final fix fix( pr test) | commisioning | Remarks
7 | done | balance by others | comments from zerone under review
8 | done | balance by others | comments from zerone under review
9 | done | balance by others | comments from zerone under review
10 | done | balance by others | comments from zerone under review
11 | done | balance by others | comments from zerone under review
12 | done | balance by others | comments from zerone under review
13 | done | balance by others | comments from zerone under review
14 | done | balance by others | comments from zerone under review
15 | done | balance by others | comments from zerone under review
16 | done | balance by others | comments from zerone under review
17 | done | balance by others | comments from zerone under review
18 | done | balance by others | comments from zerone under review
19 | done | balance by others | comments from zerone under review
20 | done | balance by others | comments from zerone under review
21 | done | balance by others | comments from zerone under review
22 | done | balance by others | comments from zerone under review
23 | done | balance by others | comments from zerone under review
24 | done | balance by others | comments from zerone under review
25 | done | balance by others | comments from zerone under review
26 | done | balance by others | comments from zerone under review
27 | done | done | comments from zerone under review
28 | done | done | comments from zerone under review
29 | done | done | comments from zerone under review
30 | done | done | comments from zerone under review
31 | done | done | comments from zerone under review
32 | done | done | comments from zerone under review
33 | done | done | comments from zerone under review
34 | done | done | comments from zerone under review
35 | done | done | comments from zerone under review
36 | done | done | comments from zerone under review
37 | done | done | comments from zerone under review
38 | done | done | comments from zerone under review
39 | done | done | comments from zerone under review
40 | done | done | comments from zerone under review
41 | done | done | comments from zerone under review
42 | done | done | n/a
43 | done | done | comments from zerone under review
44 | done | done | n/a
45 | done | done | n/a
46 | done | done | n/a
47 | done | done | n/a

## bms
Dated : 03 Mar 2013
bms commisioning
level | fcu | ahu | fans | stair case
7 | balance | n/a | n/a | n/a
8 | balance | n/a | n/a | n/a
9 | balance | n/a | n/a | n/a
10 | balance | n/a | n/a | n/a
11 | balance | n/a | n/a | n/a
12 | done | n/a | n/a | n/a
13 | done | n/a | n/a | n/a
14 | done | n/a | n/a | n/a
15 | done | n/a | n/a | n/a
16 | done | n/a | n/a | n/a
17 | done | n/a | n/a | n/a
18 | done | n/a | n/a | n/a
19 | done | n/a | n/a | n/a
20 | done | n/a | n/a | n/a
21 | done | n/a | n/a | n/a
22 | done | n/a | n/a | n/a
23 | done | n/a | n/a | n/a
24 | done | balance | balance | n/a
25 | done | n/a | n/a | n/a
26 | done | n/a | n/a | n/a
27 | done | n/a | n/a | n/a
28 | done | n/a | n/a | n/a
29 | done | n/a | n/a | n/a
30 | done | n/a | n/a | n/a
31 | done | n/a | n/a | n/a
32 | done | n/a | n/a | n/a
33 | done | n/a | n/a | n/a
34 | done | n/a | n/a | n/a
35 | done | n/a | n/a | n/a
36 | done | n/a | n/a | n/a
37 | done | n/a | n/a | n/a
38 | balance | n/a | n/a | n/a
39 | balance | n/a | n/a | n/a
40 | balance | n/a | n/a | n/a
41 | balance | n/a | n/a | n/a
42 | balance | balance | n/a | n/a
43 | balance | balance | balance | n/a
44 | balance | balance | balance | n/a
45 | balance | n/a | balance | n/a
46 | balance | balance | balance | balance
47 | n/a | n/a | n/a | n/a