## PLUMBING
Dated : 03 Mar 2013
Plumbing inspections summary (Apt shafts )
level | 1st fix(manifold +riser) | 2nd fix( pr test) | final fix( insulation) | Remarks
7 | under review | need to offer for ins | need to offer for ins
8 | under review | need to offer for ins | need to offer for ins
9 | under review | need to offer for ins | need to offer for ins
10 | under review | need to offer for ins | need to offer for ins
11 | under review | need to offer for ins | need to offer for ins
12 | under review | need to offer for ins | need to offer for ins
13 | under review | need to offer for ins | need to offer for ins
14 | under review | need to offer for ins | need to offer for ins
15 | under review | need to offer for ins | need to offer for ins
16 | under review | need to offer for ins | need to offer for ins
17 | under review | need to offer for ins | need to offer for ins
18 | under review | need to offer for ins | need to offer for ins
19 | under review | need to offer for ins | need to offer for ins
20 | under review | need to offer for ins | need to offer for ins
21 | under review | need to offer for ins | need to offer for ins
22 | under review | need to offer for ins | need to offer for ins
23 | under review | need to offer for ins | need to offer for ins
24 | under review | need to offer for ins | need to offer for ins
25 | under review | need to offer for ins | need to offer for ins
26 | under review | need to offer for ins | need to offer for ins
27 | under review | need to offer for ins | need to offer for ins
28 | under review | need to offer for ins | need to offer for ins
29 | done | need to offer for ins | need to offer for ins
30 | done | need to offer for ins | need to offer for ins
31 | done | need to offer for ins | need to offer for ins
32 | done | need to offer for ins | need to offer for ins
33 | done | need to offer for ins | need to offer for ins
34 | done | need to offer for ins | need to offer for ins
35 | done | done | need to offer for ins
36 | done | done | need to offer for ins
37 | done | done | need to offer for ins
38 | done | done | need to offer for ins
39 | done | done | need to offer for ins
40 | done | done | need to offer for ins
41 | done | done | need to offer for ins
42 | done | done | need to offer for ins
43 | done | done | need to offer for ins
44 | done | done | need to offer for ins
45 | done | done | need to offer for ins
46 | done | done | need to offer for ins
47 | done | done | need to offer for ins

## DRAINAGE
Dated : 03 Mar 2013
Drainage inspections summary(riser)
level | 1st fix | flow test | final fix( insulation) | Remarks
7 | done | need to offer done internally
8 | done | need to offer done internally
9 | done | need to offer done internally
10 | done | need to offer done internally
11 | done | need to offer done internally
12 | done | need to offer done internally
13 | done | need to offer done internally
14 | done | need to offer done internally
15 | done | need to offer done internally
16 | done | need to offer done internally
17 | done | need to offer done internally
18 | done | need to offer done internally
19 | done | need to offer done internally
20 | done | need to offer done internally
21 | done | need to offer done internally
22 | done | need to offer done internally
23 | done | need to offer done internally
24 | done | need to offer done internally
25 | done | need to offer done internally
26 | done | need to offer done internally
27 | done | need to offer done internally
28 | done | need to offer done internally
29 | done | need to offer done internally
30 | done | need to offer done internally
31 | done | need to offer done internally
32 | done | need to offer done internally
33 | done | need to offer done internally
34 | done | need to offer done internally
35 | done | need to offer done internally
36 | done | need to offer done internally
37 | done | need to offer done internally
38 | done | need to offer done internally
39 | done | need to offer done internally
40 | done | need to offer done internally
41 | done | need to offer done internally
42 | done | need to offer done internally
43 | done | need to offer done internally
44 | done | need to offer done internally
45 | done | need to offer done internally
46 | done | need to offer done internally
47 | under review

## FIRE FIGHTING
Dated : 03 Mar 2013
Fire fighting inspections summary(riser)
level | 1st fix | 2nd fix( pr test) | final fix( sprinkler,zcv,acv,fhc) | Remarks
7 | done | done | done
8 | done | done | done
9 | done | done | done
10 | done | done | done
11 | done | done | done
12 | done | done | done
13 | done | done | done
14 | done | done | done
15 | done | done | done
16 | done | done | done
17 | done | done | done
18 | done | done | done
19 | done | done | done
20 | done | done | done
21 | done | done | done
22 | done | done | done
23 | done | done | done
24 | done | done | done
25 | done | done | done
26 | done | done | done
27 | done | done | done
28 | done | done | done
29 | done | done | done
30 | done | done | done
31 | done | done | done
32 | done | done | done
33 | done | done | done
34 | done | done | done
35 | done | done | done
36 | done | done | done
37 | done | done | done
38 | done | done | done
39 | done | done | done
40 | done | done | done
41 | done | done | done
42 | done | done | done
43 | done | done | done
44 | done | done | done
45 | done | done | done
46 | done | done | done
47 | done | done | done

## HVAC
Dated : 03 Mar 2013
hvac inspections summary (riser)
level | toilet | kitchen | fresh air | stair case | grills
7 | done | done | done | need to offer | need to offer
8 | done | done | done | need to offer | need to offer
9 | done | done | done | need to offer | need to offer
10 | done | done | done | mock up done | need to offer
11 | done | done | done | need to offer | need to offer
12 | done | done | done | need to offer | need to offer
13 | done | done | done | need to offer | need to offer
14 | done | done | done | need to offer | need to offer
15 | done | done | done | need to offer | need to offer
16 | done | done | done | need to offer | need to offer
17 | done | done | done | need to offer | need to offer
18 | done | done | done | need to offer | need to offer
19 | done | done | done | need to offer | need to offer
20 | done | done | done | need to offer | need to offer
21 | done | done | done | need to offer | need to offer
22 | done | done | done | need to offer | need to offer
23 | done | done | done | need to offer | need to offer
24 | done | done | done | need to offer | need to offer
25 | done | done | done | need to offer | need to offer
26 | done | done | done | need to offer | need to offer
27 | done | done | done | need to offer | need to offer
28 | done | done | done | need to offer | need to offer
29 | done | done | done | need to offer | need to offer
30 | done | done | done | need to offer | need to offer
31 | done | done | done | need to offer | need to offer
32 | done | done | done | need to offer | need to offer
33 | done | done | done | need to offer | need to offer
34 | done | done | done | need to offer | need to offer
35 | done | done | done | need to offer | need to offer
36 | done | done | done | need to offer | need to offer
37 | done | done | done | need to offer | need to offer
38 | done | done | done | need to offer | need to offer
39 | done | done | done | need to offer | need to offer
40 | done | done | done | need to offer | need to offer
41 | done | done | done | need to offer | need to offer
42 | done | done | done | need to offer | need to offer
43 | done | done | done | need to offer | need to offer
44 | done | done | done | need to offer | need to offer
45 | done | done | done | need to offer | need to offer
46 | done | done | done | need to offer | need to offer
47 | done | done | done | need to offer | need to offer