## ELECTRICAL
TOWER - MERWEB - (AL JABER SCOPE OF WORKS) - ELECTRICAL WORKS ONLY
SR. NO. | EQUIPMENT TAG | EQUIPMENT NAME | CONTROL PANEL / VFD |  |  | CONTINUITY TEST |  |  | PRE-COMMISSIONING OF PANELS / VFDS |  |  | REMARKS
|  |  | INSTALLATION | WIR NO. | STATUS | COMPLETION OF WORKS | WIR NO. | STATUS | COMPLETION OF WORKS | WIR NO. | STATUS
AIR HANDLING UNITS
1 | L24-MW-AH1 | AHU
2 | L24-MW-AH2 | AHU
3 | L24-MW-AH3 | AHU
4 | L43-MW-AH3 AT LEVEL 43 | AHU
5 | L43-MW-AH4 AT LEVEL 42 | AHU
6 | L44-MW-AH1 | AHU
7 | L44-MW-AH2 | AHU
8 | L46-MW-AH1 | AHU
9 | L46-MW-AH2 | AHU
FANS
1 | L43-MW-EAF1 | EAF
2 | L44-MW-EAF1 | EAF
3 | L44-MW-EAF2 | EAF
4 | L44-MW-EAF3 | EAF
5 | L44-MW-EAF4 | EAF
6 | L44-MW-EAF5 | EAF
7 | L44-MW-EAF6 | EAF
8 | L44-MW-EAF1 | EAF
9 | L46-MW-FAF1 | FAF
10 | L46-MW-FAF2 | FAF
11 | L46-MW-FAF3 | FAF
12 | L46-MW-FAF4 | FAF
13 | L46-MW-FAF5 | FAF
14 | L46-MW-FAF6 | FAF
15 | L45-MW-SEF1 | SEF
16 | L45-MW-SEF2 | SEF
17 | L45-MW-SEF3 | SEF
18 | L45-MW-SEF4 | SEF
19 | L45-MW-EAF1 | SEF

## Overall Report (2)
TOWER - MERWEB - (AL JABER SCOPE OF WORKS)
EQUIPMENT TAG | EQUIPMENT NAME | SCOPE OF WORK | PRE-COMM. OF PANELS |  |  | REMARKS
|  |  | WIR NO. | DATE | STATUS
AIR HANDLING UNITS
L24-MW-AH1 | AHU | AL JABER
L24-MW-AH2 | AHU | AL JABER
L24-MW-AH3 | AHU | AL JABER
L43-MW-AH3 | AHU | AL JABER
L43-MW-AH4 | AHU | AL JABER
L44-MW-AH1 | AHU | AL JABER
L44-MW-AH2 | AHU | AL JABER
L46-MW-AH1 | AHU | AL JABER
L46-MW-AH2 | AHU | AL JABER
FANS
L44-MW-EAF1 | EAF | AL JABER
L44-MW-EAF2 | EAF | AL JABER
L44-MW-EAF3 | EAF | AL JABER
L44-MW-EAF4 | EAF | AL JABER
L44-MW-EAF5 | EAF | AL JABER
L44-MW-EAF6 | EAF | AL JABER
L44-MW-EAF1 | EAF | AL JABER
L46-MW-FAF1 | FAF | AL JABER
L46-MW-FAF2 | FAF | AL JABER
L46-MW-FAF3 | FAF | AL JABER
L46-MW-FAF4 | FAF | AL JABER
L46-MW-FAF5 | FAF | AL JABER
L46-MW-FAF6 | FAF | AL JABER

## MECHANICAL
TOWER - MERWEB - (AL JABER SCOPE OF WORKS) - MECHANICAL ONLY
SR. NO. | EQUIPMENT TAG | EQUIPMENT NAME | SCOPE OF WORK | REPLACEMENT EQUIPMENT |  | EQUIPMENT |  |  | DUCTING |  |  |  | CDP (Condensate Drain piping) |  |  |  | GRILLES/ DIFFUSERS |  |  | LOUVERS |  |  |  |  | HYDRONIC PIPING HIGH LEVEL RUN |  |  |  |  | UNIT CONN. |  |  |  | INSTRUMENTATIONS |  |  | REMARKS
|  |  |  | UNIT | QTY | INSTALLATION | WIR NO. | STATUS | INSTALLATION | INSULATION | WIR NO. | STATUS | INSTALLATION + FLOW TESTING | INSULATION | WIR NO. | STATUS | INSTALLATION | WIR NO. | STATUS | SANDTRAP | PLENUM BOX | INSULATION | WIR NO. | STATUS | INSTALLATION | PRESSURE TEST | INSULATION | WIR NO. | STATUS | VALVE PACKAGE | INSULATION | WIR NO. | STATUS | PRESSURE GAUGE, THERMOMETER, VALVES | WIR NO. | STATUS
AIR HANDLING UNITS
1 | L24-MW-AH1 | AHU | AL JABER |  |  | 100% | P3B-MEP-AC-977 | B | 100% | AL JABER NEED TO BE CONFIRMED | P3B-MEP-AC-1239A | B | NOT OFFERED FOR INSPECTION |  |  |  | N/A |  |  | NOT OFFERED FOR INSPECTION |  |  |  |  | 100% | 100% | 100% | P3B-MEP-AC-619,648 | B+B | 100% | NOT OFFERED FOR INSPECTION | P3B-MEP-AC-977 | B | NOT OFFERED FOR INSPECTION
2 | L24-MW-AH2 | AHU | AL JABER |  |  | 100% | P3B-MEP-AC-1009A | B | 100% |  | P3B-MEP-AC-1232B | B | NOT OFFERED FOR INSPECTION |  |  |  | N/A |  |  | NOT OFFERED FOR INSPECTION |  |  |  |  | 100% | 100% | 100% | P3B-MEP-AC-619,648 | B+B | 100% |  | P3B-MEP-AC-1009A | B | NOT OFFERED FOR INSPECTION
3 | L24-MW-AH3 | AHU | AL JABER |  |  | 100% | P3B-MEP-AC-1018 | B | 100% |  | NOT OFFERED FOR INSPECTION |  | NOT OFFERED FOR INSPECTION |  |  |  | N/A |  |  | NOT OFFERED FOR INSPECTION |  |  |  |  | 100% | 100% | 100% | P3B-MEP-AC-619,648 | B+B | 100% |  | P3B-MEP-AC-1018 | B | NOT OFFERED FOR INSPECTION
4 | L43-MW-AH3 AT LEVEL 43 | AHU | AL JABER |  |  | 100% | P3B-MEP-AC-1191A | W/F/R | 100% |  | P3B-MEP-AC-930A | B+C | NOT OFFERED FOR INSPECTION |  |  |  | N/A |  |  | NOT OFFERED FOR INSPECTION |  |  |  |  | 100% | 100% | 100% | P3B-MEP-AC-1191A | W/F/R | 100% |  | P3B-MEP-AC-1191A | W/F/R | NOT OFFERED FOR INSPECTION
5 | L43-MW-AH4 AT LEVEL 42 | AHU | AL JABER |  |  | 100% | P3B-MEP-AC-1295 | B | 100% |  | P3B-MEP-AC-1198 | B+C | NOT OFFERED FOR INSPECTION |  |  |  | N/A |  |  | NOT OFFERED FOR INSPECTION |  |  |  |  | 100% | 100% | 100% | P3B-MEP-AC-807,812,814 | B+A+B | 100% |  | P3B-MEP-AC-1295 | B | NOT OFFERED FOR INSPECTION
6 | L44-MW-AH1 | AHU | AL JABER |  |  | 100% | P3B-MEP-AC-1099 | B | 100% |  | P3B-MEP-AC-1116A | B | NOT OFFERED FOR INSPECTION |  |  |  | N/A |  |  | NOT OFFERED FOR INSPECTION |  |  |  |  | 100% | 100% | 100% | P3B-MEP-AC-655,,782,808 | B+A+B | 100% |  | P3B-MEP-AC-1099 | B | NOT OFFERED FOR INSPECTION
7 | L44-MW-AH2 | AHU | AL JABER |  |  | 100% | P3B-MEP-AC-1102 | B | 100% |  | P3B-MEP-AC-1142A | B | NOT OFFERED FOR INSPECTION |  |  |  | N/A |  |  | NOT OFFERED FOR INSPECTION |  |  |  |  | 100% | 100% | 100% | P3B-MEP-AC-655,,782,808 | B+A+B | 100% |  | P3B-MEP-AC-1102 | B | NOT OFFERED FOR INSPECTION
8 | L46-MW-AH1 | AHU | AL JABER |  |  | 100% | NOT OFFERED FOR INSPECTION |  |  |  | NOT OFFERED FOR INSPECTION |  | NOT OFFERED FOR INSPECTION |  |  |  | N/A |  |  | NOT OFFERED FOR INSPECTION |  |  |  |  | 100% | 100% | 100% | P3B-MEP-AC-652,810 | B+B | 100% | NOT OFFERED FOR INSPECTION |  |  | NOT OFFERED FOR INSPECTION
9 | L46-MW-AH2 | AHU | AL JABER |  |  | 100% | NOT OFFERED FOR INSPECTION |  |  |  | NOT OFFERED FOR INSPECTION |  | NOT OFFERED FOR INSPECTION |  |  |  | N/A |  |  | NOT OFFERED FOR INSPECTION |  |  |  |  | 100% | 100% | 100% | P3B-MEP-AC-652,810 | B+B | 100% | NOT OFFERED FOR INSPECTION |  |  | NOT OFFERED FOR INSPECTION
FANS
1 | L43-MW-EAF1 | EAF | AL JABER |  |  | 100% | P3B-MEP-AC-1199A | A | 100% | NOT APPLICABLE | NOT OFFERED FOR INSPECTION |  | NOT APPLICABLE | [6 empty] | NOT OFFERED FOR INSPECTION |  |  |  |  | NOT APPLICABLE
2 | L44-MW-EAF1 | EAF | AL JABER |  |  | 100% | P3B-MEP-AC-1040A | A | 100% |  | P3B-MEP-AC-804A,909,1047,1087,803A | A+B+B+A+B | [7 empty] | NOT OFFERED FOR INSPECTION
3 | L44-MW-EAF2 | EAF | AL JABER |  |  | 100% | P3B-MEP-AC-1040A | A | 100% | [10 empty] | NOT OFFERED FOR INSPECTION
4 | L44-MW-EAF3 | EAF | AL JABER |  |  | 100% | P3B-MEP-AC-1040A | A | 100% | [10 empty] | NOT OFFERED FOR INSPECTION
5 | L44-MW-EAF4 | EAF | AL JABER |  |  | 100% | P3B-MEP-AC-1040A | A | 100% | [10 empty] | NOT OFFERED FOR INSPECTION
6 | L44-MW-EAF5 | EAF | AL JABER |  |  | 100% | P3B-MEP-AC-1046 | A | 100% | [10 empty] | NOT OFFERED FOR INSPECTION
7 | L44-MW-EAF6 | EAF | AL JABER |  |  | 100% | P3B-MEP-AC-1046 | A | 100% | [10 empty] | NOT OFFERED FOR INSPECTION
8 | L44-MW-EAF1 | EAF | AL JABER |  |  | 100% | P3B-MEP-AC-1199A | A | 100% | [10 empty] | NOT OFFERED FOR INSPECTION
9 | L46-MW-FAF1 | FAF | AL JABER |  |  | 100% | P3B-MEP-AC-1103A | A | 100% |  | P3B-MEP-AC-1103A | A | [7 empty] | NOT APPLICABLE
10 | L46-MW-FAF2 | FAF | AL JABER |  |  | 100% | P3B-MEP-AC-1103A | A | 100% |  | P3B-MEP-AC-1103A | A
11 | L46-MW-FAF3 | FAF | AL JABER |  |  | 100% | P3B-MEP-AC-1103A | A | 100% |  | P3B-MEP-AC-1103A | A
12 | L46-MW-FAF4 | FAF | AL JABER |  |  | 100% | P3B-MEP-AC-1103A | A | 100% |  | P3B-MEP-AC-1103A | A
13 | L46-MW-FAF5 | FAF | AL JABER |  |  | 100% | P3B-MEP-AC-1103A | A | 100% |  | P3B-MEP-AC-1103A | A
14 | L46-MW-FAF6 | FAF | AL JABER |  |  | 100% | P3B-MEP-AC-1103A | A | 100% |  | P3B-MEP-AC-1103A | A
15 | L45-MW-SEF1 | SEF | AL JABER |  |  | 100% | P3B-MEP-AC-1082A | A | 100% |  | P3B-MEP-AC-802 | B | [7 empty] | NOT OFFERED FOR INSPECTION
16 | L45-MW-SEF2 | SEF | AL JABER |  |  | 100% | P3B-MEP-AC-1082A | A | 100% |  | P3B-MEP-AC-802 | B | [7 empty] | NOT OFFERED FOR INSPECTION
17 | L45-MW-SEF3 | SEF | AL JABER |  |  | 100% | P3B-MEP-AC-1082A | A | 100% |  | P3B-MEP-AC-802 | B | [7 empty] | NOT OFFERED FOR INSPECTION
18 | L45-MW-SEF4 | SEF | AL JABER |  |  | 100% | P3B-MEP-AC-1082A | A | 100% |  | P3B-MEP-AC-802 | B | [7 empty] | NOT OFFERED FOR INSPECTION
19 | L45-MW-EAF1 | SEF | AL JABER |  |  | 100% | P3B-MEP-AC-1082A | A | 100% |  | P3B-MEP-AC-802 | B | [7 empty] | NOT OFFERED FOR INSPECTION
NEED TO BE OFFERED FOR INSPECTION
NEED TO BE OFFERED FOR INSPECTION

## Sheet1
Level 7th |  | 1918, 2356, 2341, 2342,2280, 1914A,2353
Level 6th | L6-RO-AH5 | 1281, 2365,2366,2373,2561
| L6-RO-AH4 | 1469A,2365,2366,2137A,2367,2214,2369
| L6-RO-AH3 | 1466A,2365,2366,2137A,2367,2022A,2369
| L6-RO-AH2 | 2019,2365,2366,2137A,2367,2022A,2369
| L6-RO-AH1 | 1468A,2365,2366,2137A,2367,2022A,2369
Level 5th | L5-RO-AH1 | 1156A,2666A,2668A,2664,2776A
| L5-RO-AH3 | 1170,2666A,2668A,2567A,2301,2074,2442,2441
| L5-RO-AH6 | 1305,2666A,2668A,2301,2074,2442,2441
| L5-RO-AH2 | 1170,2666A,2668A,2567A,2442,2441
| L5-RO-AH4 | 1169B,2666A,2668A,2301,1105A,2665,2441
| L5-RO-AH5 | 1203,266A,2668A,2301,1105A,2442,2441
| L5-RO-AH8 | 1204A,2666A,2668A,2074,2442,2441
| L5-RO-AH10 | 1306A,2666A,2668A,2664,2776A
Level 4th | L4-RO-AH1 | 2203, 2827,2828,2370,2202
Level 2nd | L2-RO-AH1 | 2550b,2584,2583,2375,2371,2447
Level 1 | L1-RO-AH4 | 2057A,2586,2582,2056A,2444,2443
| L1-RO-AH3 | 2057A,2586,2582,2056,2444,2443
| L1-RO-AH2 | 2057A,2586,2582,2056,2368,2443
| L1-RO-AH1 | 2057A,2586,2582,2056,2368,2443
| L1-RO-AH7 | 2474,2705,2585,2581,2377,2575,2704A
Basement -I | B1-RO-AH3 | 2438A,2585,2581,2440,2464,2520
| B1-RO-AH5A | 2312, 2400, 2585,2581,2522,2549,2589
| B1-RO-AH2 | 2312,2383B,2382,2581,2384,2385,2491
| B1-RO-AH6 | 2437B,2585,2581,2439B,2580,2728